## RFI #12 08-18-11
Request for Information - RFI # | 12 | ROUTING | DATE SENT | VIA MAIL, EMAIL OR FAX |  |  | DATE RECEIVED | VIA MAIL, EMAIL OR FAX
|  |  |  | M | E | F |  | M | E | F
OWNER: LFMSDD |  | Contractor to Engineer | 2011-06-20 |  | X
PROJECT: HDTRWRF |  | Engineer to Contractor | 2011-08-18 |  | X
ENGINEER: GMS, Inc. |  | Copy to Owner
CONTRACTOR: Weaver General Construction Co.
RFI TITLE: Water stop at A-basin
REFERENCE: 3/AB4
CONTRACTOR'S REQUEST
The following information, interpretation, or clarification is requested as described below or in the attachments.
*(Contractor request) Baker Concrete was instructed by Jerry Miller per GMS to cut off the water stop to fit between the form and rebar leaving 2" for the concrete to bond to at the intersection ofA-Basin wall and Digester slab. Please verify
By: Jeff Burst |  |  | Date: 6/20/2011
ENGINEER'S RESPONSE
The following information, interpretation, or clarification is provided as described below or in the attachments.
The removal of 2-inches of the 4-inch normally embedded width of the waterstop at the A-Basin wall joint with the Digester floor slab is verified with this response to RFI No. 12. Two-inches of the embedded waterstop will remain in the A-Basin wall.
By: Roger J. Sams, P.E. |  |  | Date: August 18, 2011
cc: Wes Weaver, Jeff Burst, John Jacob, WGCC; Jim Heckman, LFMSDD; Tim Long, Charlie Edgar, Cindy Murray, FSD; Al Testa, CCMD; Roger Sams, Dave Frisch, Jerry Miller, GMS, Inc.; Pat Danenberg, MWI; John Peiffer, Mike Gaines, MGA; Mark Reasinger, PECI